## Sheet1
Meet The Artist
Task | Start Date | End Date | Timeline | Status
Environment Available | 2026-01-28 | 2026-01-28 | Planning | Complete
Features Timeline | 2026-01-28 | 2026-01-31 | Planning | Complete
Fix API | 2026-01-29 | 2026-02-02 | API Bug Fixing | Complete/In Progress
Update Filtering and Form Input | 2026-02-18 | 2026-03-17 | Developement | Active
Flip click animations on Cards | 2026-02-28 | 2026-03-18 | Developement | Active
Debugging Phase | 2026-03-01 | 2026-03-18 | Testing | Upcoming
Updates | 2026-03-19 | 2026-03-20 | Improvement Phase | Upcoming